## WTSC-Open-Items
WTSC Tracking List (Open Items) |  |  | 2002-01-28
Inter-carrier Test plan Action items
Item # | Test Section | Description | Responsibility | Due Date | Comments
6 | Appendix A (results matrix) | Revise appendix with Sprint contribution. | Julie Groenen | 2002-02-06 | Pending renumbering of test cases. This is now Appendix D.
7 | 911 test cases | Additional test cases (2) | Jim Grasser | 2002-03-06 | 911 test cases submitted and review. To be approved at December meeting. Part of 1.4 draft
8 | Suggest testing with two sets of MINs | Recommend testing with "native" and "foreign" MINS | Mark Wood | 2002-02-06 | Based on Jim Grasser's memo, we will insert this into the test case. Part of 1.4 draft
9 | Review PSAP/Neustar steps on 911 test cases | Determine the purpose of these steps | WTSC | 2002-03-06 | To be discussed more at March meeting
10 | Update/reorder appenices | Based on January meeting | WTSC | 2002-02-06 | To be included in Rev 1.4 draft
WTSC Action items
Item # | Topic | Description | Responsibility | Due Date | Comments
13 | Inter-carrier test guidelines | Checklist for inter-carrier testing | Ron Whitson | 2002-02-06 | General premise was accepted. A subteam will work on organization and categorizing items Edits and contributions were made in Nov. meeting
14 | Letter to NPAC - for wireline carriers | Wireline carriers have asked NPAC about wireless testing | Co-chairs | 2002-03-06 | A letter explaing wireless testing and list of resources will be sent to Neustar. Test dates will be included when finalized. Presentation made to LNPA in January
15 | Inter-carrier test dates | A suggested timeframe for testing (by region) is being created. December mtg - changed focus to provider dates | Co-chairs | 2002-02-06 | In December - we decided it would be easier for companies to provide their own test dates rather than general region dates.
16 | Pooling test cases | Do providers see a need to add pooling test cases into inter-carrier test plan? | All SPs | 2002-02-06 | Currently, we do not see a need to add test cases for pooled numbers since network will view these the same as ported numbers and test cases are already in place. Ask each SP to review and provide comments for Dec meeting.
17 | 911 discussion in March | Companies to invite SMEs to attend in March | WTSC | 2002-03-05
Items at WNPO
1 | Vendor compliance | Concern that SCP/STP vendors will not be able to provision SMS routing | WNPO | 2002-01-15 | Sent to WNPO - Letters are being sent to vendors to discuss how they will be compliant. 1/7 - Team decided each carrier must pursue this.
3 | Letter to LLC regarding NPAC release 3.1 | Delay of NPAC release 3.1 may hamper inter-carrier testing | WNPO | 2001-11-07 | WNPO will send advisory letter to LLC to keep regions in order. Not applicable anymore since test team is not using 3.1 guidelines.
4 | Cause code 26 & NP reserve 1 | Do wireless switches require cause code 26 to be delivered? Is NP reserve software required on wireless switches? | WNPO | 2001-11-28 | Based on input from WNPO and other carriers, will we need to write test cases. A "cause code suppression" project is being discussed.

## WTSC-Closed Items
WTSC Tracking List (Closed Items)
Test Plan Changes
Item # | Topic | Description | Responsibility | Due Date | Date Closed | Comments
1 | 4.0/ICC | ICC test cases | T. Patton (lead) | 6/29/2001 7/26/01 | 2001-08-08 | Need to revise item about OSP receiving confirmation. Teresa will send edits to co-chairs. Changes will be sent with all 4.0 changes. (see #5). No changes necessary - CLOSED
2 | Call completion tests Test matrix - revised | Test scenarios | Mark Wood | 7/26/2001 8/8/01 8/23/01 | 2001-09-04 | Create test cases based on "ported from" criteria. This will cause additional test cases to be created. Mark W. sent out suggestions on 6/22/01 to team. General document accepted in Denver on 8/8/01. Some editing will be done for review on 8/23/01. Test matrix approved with Revision 1.3 (9/4)
3 | All sections | Link test cases together (see related document sent out) | Jim Grasser | 7/26/2001 8/8/01 8/23/01 | 2001-09-04 | Jim will submit a few test scenarios to be included in test document. Sent to WTSC on 6/27/01 for review. General document accepted in Denver on 8/8/01. Some editing will be done for review on 8/23/01. Approved with Revision 1.3 (9/4)
4 | New section (4.6) | GTT test cases | Mark Wood (lead) | 7/26/2001 8/8/01 8/23/01 | 2001-09-04 | Ad hoc team working on this. Team met in Denver on 8/6/01. Test cases were agreed upon by ad hoc team and regular test team. These will be inserted as version 1.3 for review. Approved with Revision 1.3 (9/4)
5 | Section 4.0 | 4.0 - standardize language | T. Patton (lead) | 7/26/2001 8/8/01 8/23/01 | 2001-09-04 | Draft changes sent to ad hoc team. Conference call scheduled for 6/29/01. Teresa reviewed entire section on 4.0 in Denver on 8/7/01. Edits will be made and presented for final confimation on 8/23/01. Approved with Revision 1.3 (9/4)
7 | Section 4.3 | Need to resolve confusion of certain test cases. | Mark Wood (lead) | 7/26/2001 8/8/01 8/23/01 | 2001-09-04 | Mark will work on this based on other's contribution. Sent out to team for suggestion on 6/22/01. Wording was agreed upon in Denver on 8/7/01. Changes will be made in version 1.3 for final review on 8/23/01 Approved with Revision 1.3 (9/4)
8 | Section 4.4 (old) | Change to 4.5 | Mark Wood (lead) | 2001-08-23 | 2001-09-04 | See #13. Approved with Revision 1.3 (9/4)
9 | Section 4.5 (new) | Add test case | Mark Wood (lead) | 2001-08-23 | 2001-09-04 | See #13. Approved with Revision 1.3 (9/4). Same as #12.
10 | Section 4.4 (new) | Wireline-wireline test cases | Ron Whitson | 2001-08-23 | 2001-09-04 | See #13. Approved with Revision 1.3 (9/4)
11 | Section 4.1, 2, 3 | Remove "local" from test cases | Mark Wood (lead) | 2001-08-23 | 2001-09-04 | See #13. Approved with Revision 1.3 (9/4)
12 | New test case (4.5.7) | Operator service - while roaming | Mark Wood (lead) | 2001-08-23 | 2001-09-04 | See #13. Approved with Revision 1.3 (9/4)
13 | Test Plan - Version 1.3 | Changes wil be incorporated into next version. | Mark Wood (lead) | 2001-08-23 | 2001-09-04 | Contributions above will be made as version 1.3. This will be sent out to the team by 8/17/01 for review on our conference call on 8/23/01. Approved at mtg in Tampa (9/4)
Other items
Item # | Topic | Description | Responsibility | Due Date | Date Closed | Comments
1 | Meeting host | Need company to host September meeting | Co-chairs | 2001-07-01 | 2001-06-27 | Request to 3rd company has been made. TSI has agreed to host in Tampa, FL.
2 | Vendor compliance | Concern that SCP/STP vendors will not be able to provision SMS routing | Co-chairs/WNPO | 6/22/2001 1/15/02 | 2001-10-11 | Item moved to WNPO list
3 | Test MSAs/dates | SPOCs should submit their companies test markets and date readiness to co-charis | Test SPOCs | 8/7/2001 8/31/01 | 2001-09-04 | Test markets should start to be identified for August meeting. 8/8/01 - companies should at least identify their test markets, even if they do not know the dates. This will be an ongoing issue until 11/24/02.
4 | Draft letter - to nonparticipating companies | A letter will be sent to all carriers in the top 100 MSAs that are not participating in our meeting. | Gene Perez (lead) | 8/23/2001 9/5/01 | 2001-09-04 | Based on list of carriers in top 100 to be sent by Jim Grasser. Document will be finalized after Tampa meeting. Letter revised and approved.
5 | Comments to IITC (Internetwork Interoperability Test Coordination) regarding role in testing | IITS made presentation at Denver meeting about doing performance testing for carriers. | All carriers | 8/23/2001 9/5/01 | 2001-09-04 | Companies had questions about financing, timing, resources, etc. These will be sent to IITC for answers at next meeting. Impact of WNP has been discussed, IITC will monitor team issues ongoing.
6 | Submit reasons for not being able to complete testing by 5/31/02 (ex: - vendor delay, resources, etc.) | Most carriers do not believe they will meet the industry guideline for testing. | All carriers | 2001-09-04 | 2001-09-04 | Survey related to #4 was reviewed and approvied (afer updates).
7 | Risk for not meeting test deadline | Related to #6 | Gerry Scillitani | 2001-09-05 | 2001-09-04 | Revised documnt sent out. Will finalize in Tampa. Document sent to WNPO on 9/7
8 | Meeting sites/dates for 2002 | Need volunteers to host meetings from Jan-Jun 2002 | All carriers | 2001-10-03 | 2001-11-01 | Sites have been set through June 2002, with the exception of January. January meeting finalized.
9 | Send letter (#4) out to nonparticipating companies | Need volunteers to contact service providers. | WTSC team | 2001-10-03 | 2001-09-21 | Gene Perez will lead the effort to mail and receive letters from carriers. CLOSED - Letters sent out on 9/21.
10 | Top 100 MSA list | Question as to which top 100 MSA list applies to mandate | WNPO | 2001-09-07 | 2001-09-14 | Jim Grasser reported that same list used for wireline porting will be used for wireless porting.
11 | Bona Fide Requests | Confusion over time alloted for BFR in different scenarios | WNPO | 2001-10-03 | 2001-10-03 | To be reviewed at Dallas meeting (10/2). Issue was claified regarding carriers "supporting" LNP. Carriers will most likely receive request to open all codes on 11/24/02
12 | Wireline SOAs | SOAs do not popluate time field, only date field during concurrence | WNPO | 2001-11-06 | 2001-10-15 | Item moved to WNPO list. This will be discussed at next WNPO meeting. Proposal to use 00:00 when wireline carrier is involved.