## WTSC-Open-Items
WTSC Tracking List (Open Items)
Inter-carrier Test plan changes
Item # | Test Section | Description | Responsibility | Due Date | Comments
1 | 4.0/ICC | ICC test cases | T. Patton (lead) | 6/29/2001 7/26/01 | Need to revise item about OSP receiving confirmation. Teresa will send edits to co-chairs. Changes will be sent with all 4.0 changes. (see #5)
2 | Call completion tests | Test scenarios | Mark Wood | 2001-07-26 | Create test cases based on "ported from" criteria. This will cause additional test cases to be created. Mark W. sent out suggestions on 6/22/01 to team.
3 | All sections | Link test cases together (see related document sent out) | Jim Grasser | 2001-07-26 | Jim will submit a few test scenarios to be included in test document. Sent to WTSC on 6/27/01 for review.
4 | New section | GTT test cases | Mark Wood (lead) | 2001-08-07 | Ad hoc team working on this
5 | Section 4.0 | 4.0 - standardize language | T. Patton (lead) | 2001-07-26 | Draft changes sent to ad hoc team. Conference call scheduled for 6/29/01.
6 | Appendix A | Revise appendix with Sprint contribution. | Julie Groenen | 2001-08-07 | Pending renumbering of test cases.
7 | Section 4.3 | Need to resolve confusion of certain test cases. | Mark Wood (lead) | 2001-07-26 | Mark will work on this based on other's contribution. Sent out to team for suggestion on 6/22/01.
Other items
Item # | Topic | Description | Responsibility | Due Date | Comments
2 | Vendor compliance | Concern that SCP/STP vendors will not be able to provision SMS routing | Co-chairs/WNPO | 2001-06-22 | Sent to WNPO - Letters are being sent to vendors to discuss how they will be compliant.Will return feedback to WTSC.
3 | Test MSAs/dates | SPOCs should submit their companies test markets and date readiness to co-charis | Test SPOCs | 2001-08-07 | Test markets should start to be identified for August meeting.

## WTSC-Closed Items
WTSC Tracking List (Closed Items)
Test Plan Changes
Item # | Topic | Description | Responsibility | Due Date | Date Closed | Comments
Other items
Item # | Topic | Description | Responsibility | Due Date | Date Closed | Comments
1 | Meeting host | Need company to host September meeting | Co-chairs | 2001-07-01 | 2001-06-27 | Request to 3rd company has been made. TSI has agreed to host in Tampa, FL.