## Open
Date | Issue | Comments | Owner | Status
2004-02-05 | Team to come back with feedback regarding proposal to have formal interoperability testing between vendors and/or SP’s. | Carriers are invited to reflect on the need and bring up at WTSC if see a need for this. Watch item over next few months. |  | Holding Pattern
Team
2004-02-05 | Team to share tests scheduled and results | Carriers to return test scheduled via template to Julie once she sends out | Team | On-going
2004-03-18 | Team to submit ideas to cover on April 1st Kick-Off call for small carriers | By 3/25 would be best | Team | Open

## Closed
Date | Issue | Comments | Owner | Status
2004-01-22 | Julie to check with CTIA regarding sending our letter, getting small carrier contacts and about a small carrier Critical Issues Forum | Update: 1/23: Julie has asked about CTIA distributing our letter. Lori Messing from CTIA stated they are tentatively planning a Critical Issues Forum March 17th. She is also looking into providing WTSC a workable small carrier contact list. 3/4/04: Julie to send out information on the forum. | Julie G | Closed
2004-01-22 | Julie to edit carrier participation letter for WTSC review | Update 1/29/04: Letter edited and a 2nd version sent out 1/29 for review in 2/5 WTSC meeting. | Julie G | Closed
2004-01-29 | Jean Anthony to write up a paragraph or two regarding interoperability testing for WTSC to discuss 2/5/04. | Done | Jean Anthony | Closed
2004-02-02 | How will WTSC structure on-going for new WICIS releases? | One WNPO recommendation was to have OBF go back to WNPO members who would get appropriate company contact to test. Confirm 2/19 WTSC ok with this. | Team | Closed
2004-03-04 | Julie to send out the RCR wireless link to team | Done | Julie G | Closed
2004-03-04 | Julie to post on www.npac.com WTSC link how to get on WTSC distribution list. | E-mailed Neustar | Julie G | Complete
2004-03-04 | Julie to reach out to TSI (Rob Smith), Neustar (Gene Johnston) & Verisign (Maggie Lee) to join WTSC call next week re communication for release of vendor releases. | Vendors would not publish their releases unless it involves an industry affecting change, ie. WICIS. Industry would use the same process now (WTSC) or WNPO (post 5/24/04) to cooredinate testeing. Individual carriers may decide to reach out to each other as necessary to test various individual vendor releases. | Julie G | Closed