## WLNP ICP Test Schedule
LAST UPDATE: | 2003-05-06 |  | This schedule is updated monthly after WTSC meetings
WTSC ICP TESTING SCHEDULE
Sched Test Start Date | Testing Carriers | Test Type | MSA (optional) | STATUS | Status Date | NPAC Environment | WICIS LVL | Note
2003-03-11 | Sprint - Cingular |  | Releigh | Complete |  | Test | 1
2003-03-13 | Sprint - US Cellular (USC) | ICP | Manchester | Complete | 2003-03-19 | Test | 1
2003-04-14 | Verizon (VZW) - USC | ICP | Releigh | Complete | 2003-04-14 | Test | 1 | not classified as successful retest to be scheduled
2003-04-14 | AT&T Wireless (AWS) - USC | ICP | Releigh | Complete | 2003-04-15 | Test | 1 | not classified as successful retest to be scheduled
2003-04-21 | AWS - VZN | ICP | Releigh | Complete |  | Test | 1 | not classified as successful retest to be scheduled
4/31/03 | Cingular - SBC |  | Hartford | Canceled |  |  |  | pending reschedule
May
2003-05-12 | Nextel - Sprint | ICP | Chicago |  |  | Test | 1
2003-05-19 | USC - Nextel - Nextel Partners (NP) | ICP | TBD |  |  | Test | 1
2003-05-19 | USC - Rural Cellular | LTI | Bangor,ME |  |  | Test | 1
2003-05-26 | Nextel - Cingular | ICP | Dallas | Pending
2003-05-26 | Nextel - VZW - NP | ICP | New York
2003-05-26 | Cingular - VZW | ICP |  | Pending
June
2003-06-13 | AWS - Nextel - NP | ICP |  |  |  | Test | 2
2003-06-23 | Cingular -VZW | ICP |  |  |  | Prod | 1
July
2003-07-07 | Sprint PCS - Rural Cellular | LTI | Minnesota |  |  | Test | 2
2003-07-21 | VZW - Sprint | ICP |  |  |  | Test | 2
2003-07-28 | Sprint - Nextel | ICP | TBD |  |  | Prod | 2
Aug
Aug | Qwest - Nextel | ICP |  | Date Pndg |  |  | 2
2003-08-18 | Sprint PCS - Qwest | ICP | Denver |  |  | Prod | 2
2003-08-25 | Cingular - US Cellular | Test | TBD |  |  | Test | 2
Sept
Sept or Oct | QWEST-Nextel - NP | E2E | Minneapolis |  |  | Prod | 2 | Includes Qwest wireline & wireless
Sept | Cingular - VZW | E2E | DC/Baltimore |  |  | Prod | 2
2003-09-02 | AWS, VZW, Cingular, SBC, Nextel, T-Mobile, Sprint PCS | Round Robin | LA |  |  | Prod | 2
2003-09-15 | AWS, VZW, Cingular, Nextel, T-Mobile, Sprint PCS,USC | Round Robin | Chicago |  |  | Prod | 2
2003-09-15 | AWS - Sprint PCS | ICP |  |  |  | Test | 2
2003-09-15 | VZN - USC | E2E | Chi, Detroit, Clev. |  |  | Prod | 2
OCT
2003-10-06 | Sprint - AWS | ICP | Las Vegas |  |  | Prod | 2
2003-10-20 | Sprint - USC | ICP | Chicago |  |  | Test | 2
2003-10-27 | Sprint - Cingular | E2E | Orlando |  |  | Prod | 2
NOV
2003-11-17 | SPCS - SLTD | ICP |  |  |  | Test | 2
None | Cingular - T-Mobile - VZW | ICP / E2E | Atlanta |  |  | Test / Prod
None | VZW - SBC | ICP | Detroit
None | USC - Cingular | E2E |  |  |  | Prod
None | AWZ - VZN - USC | ICP |  |  |  | Test | 2
None | USC - T-Mobile | ICP |  |  |  | Test | 2
None | USC - Altell | ICP |  |  |  | Test | 2
|  | ICP |  | Firm |  | Test
|  | E2E |  | Complete |  | Prod
|  | Round Robin |  | Pending |  | both
In-Process

## WLNP Network Test Schedule
LAST UPDATE: | 2003-03-11
NETWORK TESTING SCHEDULE
Schedules reviewed/updated at each WTSC meeting
MSA | MSA # | NPAC Region | Total Carriers Testing in MSA | Test schedule Updates 1/13/03 | STATUS | Status Date
Indianapolis, IN MSA | 29 | MW | 3 | TBD SBC, Cingular, AWS | TBD
Washington--Baltimore, DC--MD--VA--WV CMSA | 4 | MA | 5
Detroit--Ann Arbor--Flint, MI CMSA | 8 | MW | 1 |  |  | 2003-03-11
Atlanta, GA MSA | 11 | SE | 1 |  |  | 2003-03-11
Chicago--Gary--Kenosha, IL--IN--WI CMSA | 3 | MW | 2 | 1/15/03, USCellular, Sprint PCS (Ntwk) | Complete | 2003-03-11
Seattle--Tacoma--Bremerton, WA CMSA | 13 | WE | 2 | 10/01/02 AWS, Qwest Wireless | Complete | 2002-10-01
Portland--Salem, OR--WA CMSA | 23 | WE | 0 | 10/01/02 AWS, Qwest Wireless | Complete | 2002-10-01
Milwaukee--Racine, WI CMSA | 27 | MW | 2 | 9/16/02 Telecorp PCS, US Cellular | Complete | 2002-09-16
Orlando, FL MSA | 28 | SE | 3 | Sprint LTD, Sprint PSC, AWS Complete 10/02. | Complete | 2002-10-02
Las Vegas, NV--AZ MSA | 32 | WC | 5 | AWS, Cingular, Sprint PCS, Sprint Wireline, VZW | Complete | 2002-07-15
Hartford, CT MSA | 42 | NE | 2 | 1/6/03 AWS & SBC | Complete | 2003-01-06
Knoxville, TN MSA | 63 | SE | 2 | 10/03/02 USC , Telecorp PCS | Complete | 2002-10-03
Des Moines, IA MSA | 91 | WE | 2 | 8/19/02 USC, Telecorp PCS | Complete | 2002-08-18
New York--Northern New Jersey--Long Island, NY--NJ--CT--PA CMSA | 1 | NE | 0 | 4/28/03 Nextel,Sprint PCS, AWS, T-Mobile, Verizion Wireless | Canceled | 2003-03-11
Los Angeles--Riverside--Orange County, CA CMSA | 2 | WC | 0 | 5/12/03 SBC, Verizon Wireless, AWS, Nextel?, Cingular? 8/03 AWS, Verizon Wireless WICIS 2.0 regression | Canceled | 2003-03-11
San Francisco--Oakland--San Jose, CA CMSA | 5 | WC | 0
Philadelphia--Wilmington--Atlantic City, PA--NJ--DE--MD CMSA | 6 | MA | 0
Boston--Worcester--Lawrence, MA--NH--ME--CT CMSA | 7 | NE | 0
Dallas--Fort Worth, TX CMSA | 9 | SW | 0 | 3/31/03 Nextel?, SBC, Cingular, AWS, 5/1/03 Nextel, Sprint PCS
Houston--Galveston--Brazoria, TX CMSA | 10 | SW | 0
Miami--Fort Lauderdale, FL CMSA | 12 | SE | 0
Phoenix--Mesa, AZ MSA | 14 | WE | 0
Minneapolis--St. Paul, MN--WI MSA | 15 | WE | 0
Cleveland--Akron, OH CMSA | 16 | MW | 0
San Diego, CA MSA | 17 | WC | 0
St. Louis, MO--IL MSA | 18 | SW | 0
Denver--Boulder--Greeley, CO CMSA | 19 | WE | 0
San Juan--Caguas--Arecibo, PR CMSA | 20 | SE | 0
Tampa--St. Petersburg--Clearwater, FL MSA | 21 | SE | 0
Pittsburgh, PA MSA | 22 | MA | 0
Cincinnati--Hamilton, OH--KY--IN CMSA | 24 | MW | 0 | Verizon Wireless looking for test partner.
Sacramento--Yolo, CA CMSA | 25 | WC | 0
Kansas City, MO--KS MSA | 26 | SW | 0
San Antonio, TX MSA | 30 | SW | 0
Norfolk--Virginia Beach--Newport News, VA--NC MSA | 31 | MA | 0
Columbus, OH MSA | 33 | MW | 0
Charlotte--Gastonia--Rock Hill, NC--SC MSA | 34 | SE | 0
New Orleans, LA MSA | 35 | SE | 0
Salt Lake City--Ogden, UT MSA | 36 | WE | 0
Greensboro--Winston-Salem--High Point, NC MSA | 37 | SE | 0
Austin--San Marcos, TX MSA | 38 | SW | 0
Nashville, TN MSA | 39 | SE | 0
Providence--Fall River--Warwick, RI--MA MSA | 40 | NE | 0
Raleigh--Durham--Chapel Hill, NC MSA | 41 | SE | 0
Buffalo--Niagara Falls, NY MSA | 43 | NE | 0
Memphis, TN--AR--MS MSA | 44 | SE | 0
West Palm Beach--Boca Raton, FL MSA | 45 | SE | 0
Jacksonville, FL MSA | 46 | SE | 0
Rochester, NY MSA | 47 | NE | 0
Grand Rapids--Muskegon--Holland, MI MSA | 48 | MW | 0
Oklahoma City, OK MSA | 49 | SW | 0
Louisville, KY--IN MSA | 50 | SE | 0
Richmond--Petersburg, VA MSA | 51 | MA | 0
Greenville--Spartanburg--Anderson, SC MSA | 52 | SE | 0
Dayton--Springfield, OH MSA | 53 | MW | 0
Fresno, CA MSA | 54 | WC | 0
Birmingham, AL MSA | 55 | SE | 0
Honolulu, HI MSA | 56 | WC | 0
Albany--Schenectady--Troy, NY MSA | 57 | NE | 0
Tucson, AZ MSA | 58 | WE | 0
Tulsa, OK MSA | 59 | SW | 0
Syracuse, NY MSA | 60 | NE | 0
Omaha, NE--IA MSA | 61 | WE | 0
Albuquerque, NM MSA | 62 | WE | 0
El Paso, TX MSA | 64 | SW | 0
Bakersfield, CA MSA | 65 | WC | 0
Allentown--Bethlehem--Easton, PA MSA | 66 | MA | 0
Harrisburg--Lebanon--Carlisle, PA MSA | 67 | MA | 0
Scranton--Wilkes-Barre--Hazleton, PA MSA | 68 | MA | 0
Toledo, OH MSA | 69 | MW | 0
Baton Rouge, LA MSA | 70 | SE | 0
Youngstown--Warren, OH MSA | 71 | MW | 0
Springfield, MA MSA | 72 | NE | 0
Sarasota--Bradenton, FL MSA | 73 | SE | 0
Little Rock--North Little Rock, AR MSA | 74 | SW | 0
McAllen--Edinburg--Mission, TX MSA | 75 | SW | 0
Stockton--Lodi, CA MSA | 76 | WC | 0
Charleston--North Charleston, SC MSA | 77 | SE | 0
Wichita, KS MSA | 78 | SW | 0
Mobile, AL MSA | 79 | SE | 0
Columbia, SC MSA | 80 | SE | 0
Colorado Springs, CO MSA | 81 | WE | 0
Fort Wayne, IN MSA | 82 | MW | 0
Daytona Beach, FL MSA | 83 | SE | 0
Lakeland--Winter Haven, FL MSA | 84 | SE | 0
Johnson City--Kingsport--Bristol, TN--VA MSA | 85 | SE | 0
Lexington, KY MSA | 86 | SE | 0
Augusta--Aiken, GA--SC MSA | 87 | SE | 0
Melbourne--Titusville--Palm Bay, FL MSA | 88 | SE | 0
Lancaster, PA MSA | 89 | MA | 0
Chattanooga, TN--GA MSA | 90 | SE | 0
Kalamazoo--Battle Creek, MI MSA | 92 | MW | 0
Lansing--East Lansing, MI MSA | 93 | MW | 0
Modesto, CA MSA | 94 | WC | 0
Fort Myers--Cape Coral, FL MSA | 95 | SE | 0
Jackson, MS MSA | 96 | SE | 0
Boise City, ID MSA | 97 | WE | 0
Madison, WI MSA | 98 | MW | 0
Spokane, WA MSA | 99 | WE | 0
Pensacola, FL MSA | 100 | SE | 0
Evansville IN* | 133 | MW | 0
Lubbock, TX* | 151 | SW | 0
No Market Selected yet - Review at WTSC Mthly Mtg
T-Mobile, Cingular, Nextel to perform Network and E2E
Rural Cellular-looking for test numbers in Minnesota and Bangor