## WLNP I-C test schedule (NEW)
LAST UPDATE: | 2002-05-29
|  |  |  | Carrier - Ready Date (Test RATECENTER) | Carrier - Ready Date (Test RATECENTER) | Carrier - Ready Date (Test RATECENTER) | Carrier - Ready Date (Test RATECENTER) | Carrier - Ready Date (Test RATECENTER) | Carrier - Ready Date (Test RATECENTER) | Carrier - Ready Date (Test RATECENTER)
MSA | MSA # | NPAC Region | Total Carriers Testing in MSA | January-March | April | May | June | July | August | September | NO DATES | I-C Testing
Chicago--Gary--Kenosha, IL--IN--WI CMSA | 3 | MW | 5 |  | July: Nextel - 7/15/02; Cingular - 7/15/02 (CHICGOZN01); Voicestream - 7/15/02; August: U.S. Cellular - 8/15/02; September: Nextel - 9/2/02 - IC TESTING | Verizon Wireless | 2002-07-15
Dallas--Fort Worth, TX CMSA | 9 | SW | 5 |  |  |  | Nextel - 6/1/02 NETWORK ONLY AT&T Wireless - 6/24/02 (GRANDPRARI, MCKINNEY, ARLINGTON) | Cingular - 7/15/02 (IRVING, GLENDALE); Voicestream - 7/15/02 | Sprint PCS - 8/15/02 (IRVING, GLENDALE); | Nextel - 9/2/02 - IC TESTING |  | 2002-07-15
Washington--Baltimore, DC--MD--VA--WV CMSA | 4 | MA | 5 |  | July: AT&T Wireless - 7/16/02 (BALTIMORE, BELAIR); Cingular - 7/15/02 (CATONSVIL, WSHNGTONZN1); Sprint PCS - 7/15/02; August: U.S. Cellular - 8/15/02 (HAGERSTOWN); Voicestream - 8/15/02 | Verizon Wireless | 2002-07-15
Las Vegas, NV--AZ MSA | 32 | WC | 5 | Sprint Wireline 1/2/02 (LAS VEGAS) | July: AT&T Wireless - 7/15/02 (LAS VEGAS); Cingular 7/29/02 (LSAN DA 01); Sprint PCS - 7/15/02 (LAS VEGAS) | Verizon Wireless | 2002-07-29
Orlando, FL MSA | 28 | SE | 4 | Sprint Wireline 1/2/02 (KISSIMMEE & WINTERPARK) | July: Cingular - 7/10/02; AT&T Wireless-7/22/02 (ORLANDO, KISSIMMEE); August: Sprint PCS - 8/15/02 (KISSIMMEE, WINTER PARK) |  | 2002-07-22
New York--Northern New Jersey--Long Island, NY--NJ--CT--PA CMSA | 1 | NE | 3 |  | July: Voicestream - 7/15/02; August: AT&T Wireless -8/5/02 (TORRINGTON, CLINTON) | Verizon Wireless | 2002-08-05
Atlanta, GA MSA | 11 | SE | 2 |  | July: Cingular - 7/10/02; Voicestream - 7/15/02 |  | 2002-07-15
Los Angeles--Riverside--Orange County, CA CMSA | 2 | WC | 2 |  | July: Sprint PCS-7/15/02 (LSAN DA 01) | Verizon Wireless | 2002-07-15
| 12 | SE | 2 |  | July: Cingular - 7/10/02; AT&T Wireless - 7/16/02 (MIAMI); |  | 2002-07-16
Seattle--Tacoma--Bremerton, WA CMSA | 13 | WE | 2 |  | July: AT&T Wireless - 7/15/02 (WHATCOMCTY, RENTON); August: Qwest Wireless - 8/1/02 |  | 2002-08-01
Hartford, CT MSA | 42 | NE | 2 |  | June: AT&T Wireless - 6/24/02 (HARTFORD); August: Cingular - 8/5/02 (HARTFORD) |  | 2002-08-05
Indianapolis, IN MSA | 29 | MW | 2 |  | July: Cingular - 7/10/02; August: AT&T Wireless - 8/5/02 (INDIANAPOLIS) |  | 2002-08-05
Knoxville, TN MSA | 63 | SE | 2 |  | June: U.S. Cellular - 6/1/02 - NETWORK (KNOXVILLE); July: Telecorp PCS - 7/30/02 - (KNOXVILLE); August: U.S. Cellular - 8/15/02 (KNOXVILLE) |  | 2002-08-15
Milwaukee--Racine, WI CMSA | 27 | MW | 2 |  | June: Telecorp PCS - 6/30/02 (MILWAUKZN 1); August: U.S. Cellular - 8/15/02 (MILWAUKEE ZONE 1 & 2) |  | 2002-08-15
Raleigh--Durham--Chapel Hill, NC MSA | 41 | SE | 2 |  | July: Cingular - 7/10/02; August: U.S. Cellular - 8/15/02 (DUNN, SMITHFIELD) |  | 2002-08-15
Des Moines, IA MSA | 91 | WE | 2 |  | August: Sprint PCS (DES MOINES) - 8/15/02; Telecorp PCS - 8/30/02 - (DES MOINES); U.S. Cellular - 8/15 (NETWORK ONLY); |  | 2002-08-30
Johnson City--Kingsport--Bristol, TN--VA MSA | 85 | SE | 2 | Sprint Wireline 1/2/02 (JOHNSON CY) | August: Triton - 8/30/02 |  | 2002-08-30
Little Rock--North Little Rock, AR MSA | 74 | SW | 2 |  | August: Telecorp PCS - 8/30/02 (LITTLE ROCK); September: ALLTEL - 9/02 - Network (LITTLEROCK) |  | 2002-09-02
Mobile, AL MSA | 79 | SE | 2 |  | August: Telecorp PCS - 8/30/02 (MOBILE); September: ALLTEL - 9/02 - Network (MOBILE) |  | 2002-09-02
Boston--Worcester--Lawrence, MA--NH--ME--CT CMSA | 7 | NE | 2 | [7 empty] | Verizon Wireless | TBD
Charlotte--Gastonia--Rock Hill, NC--SC MSA | 34 | SE | 2 | [7 empty] | Verizon Wireless | TBD
Columbus, OH MSA | 33 | MW | 2 | [7 empty] | Verizon Wireless | TBD
Detroit--Ann Arbor--Flint, MI CMSA | 8 | MW | 2 | [7 empty] | Verizon Wireless | TBD
Minneapolis--St. Paul, MN--WI MSA | 15 | WE | 2 | [7 empty] | Verizon Wireless | TBD
Spokane, WA MSA | 99 | WE | 2 | [7 empty] | Verizon Wireless | TBD
New Orleans, LA MSA | 35 | SE | 1 |  | June: Telecorp PCS - 6/30/02 (NEW ORLEANS, LK CHARLES) |  | 2002-06-30
Portland--Salem, OR--WA CMSA | 23 | WE | 1 |  | July: AT&T Wireless - 7/15/02 (PORTLAND) |  | 2002-07-15
West Palm Beach--Boca Raton, FL MSA | 45 | SE | 1 |  | July: AT&T Wireless - 7/16/02 (WPALMBEACH) |  | 2002-07-16
Charleston--North Charleston, SC MSA | 77 | SE | 1 |  | July: Triton - 7/30/02 |  | 2002-07-30
Columbia, SC MSA | 80 | SE | 1 |  | July: Sprint PCS - 7/15/02 ; Triton - 7/30/02 |  | 2002-07-30
Greenville--Spartanburg--Anderson, SC MSA | 52 | SE | 1 |  | July: Triton - 7/30/02 |  | 2002-07-30
Jackson, MS MSA | 96 | SE | 1 |  | July: Telecorp PCS - 7/30/02 (JACKSON) |  | 2002-07-30
Norfolk--Virginia Beach--Newport News, VA--NC MSA | 31 | MA | 1 |  | July: Triton - 7/30/02 |  | 2002-07-30
Richmond--Petersburg, VA MSA | 51 | MA | 1 |  | July: Triton - 7/30/02 |  | 2002-07-30
Denver--Boulder--Greeley, CO CMSA | 19 | WE | 1 |  | August: Qwest Wireless - 8/1/02 |  | 2002-08-01
Phoenix--Mesa, AZ MSA | 14 | WE | 1 |  | August: Qwest Wireless - 8/1/02 |  | 2002-08-01
Houston--Galveston--Brazoria, TX CMSA | 10 | SW | 1 |  | August: Voicestream - 8/15/02 |  | 2002-08-15
Lubbock, TX* | 151 | SW | 1 |  | August: Cingular - 8/15/02 (LUBBOCK) |  | 2002-08-15
Madison, WI MSA | 98 | MW | 1 |  | August: U.S. Cellular - 8/15/02 |  | 2002-08-15
Salt Lake City--Ogden, UT MSA | 36 | WE | 1 |  | August: Voicestream -8/15/02 |  | 2002-08-15
Tulsa, OK MSA | 59 | SW | 1 |  | August: U.S. Cellular - 8/15/02 (NEWORK ONLY) |  | 2002-08-15
Augusta--Aiken, GA--SC MSA | 87 | SE | 1 |  | August: Triton - 8/30/02 |  | 2002-08-30
Birmingham, AL MSA | 55 | SE | 1 |  | August: Telecorp PCS - 8/30/02 (BIRMINGHAM) |  | 2002-08-30
Evansville IN* | 133 | MW | 1 |  | August: Telecorp PCS - 8/30/02 (EVANSVILLE) |  | 2002-08-30
Louisville, KY--IN MSA | 50 | SE | 1 |  | August: Telecorp PCS - 8/30/02 (LOUISVILLE) |  | 2002-08-30
Memphis, TN--AR--MS MSA | 44 | SE | 1 |  | August: Telecorp PCS - 8/30/02 (MEMPHIS, JONESBORO) |  | 2002-08-30
Nashville, TN MSA | 39 | SE | 1 |  | August: Telecorp PCS - 8/30/02 (NASHVILLE) |  | 2002-08-30
San Juan--Caguas--Arecibo, PR CMSA | 20 | SE | 1 |  | August: Telecorp PCS - 8/30/02 (SANTRUCE) |  | 2002-08-30
Albuquerque, NM MSA | 62 | WE | 1 |  | September: ALLTEL - 9/02 - Network (ALBUQUERQUE); Sprint PCS - 9/15/02 (ALBUQUERQUE) |  | 2002-09-15
Hutchinson, KS* | x | SW | 1 |  | September: ALLTEL - 9/02 - Network (HUTCHINSON) |  | 2002-09-02
Jacksonville, FL MSA | 46 | SE | 1 |  | September: ALLTEL - 9/02 - Network (JACKSONVL) |  | 2002-09-02
Toledo, OH MSA | 69 | MW | 1 |  | September: ALLTEL - 9/02 - Network (TOLEDO) |  | 2002-09-02
Youngstown--Warren, OH MSA | 71 | MW | 1 | [7 empty] | Dobson Cellular | TBD
Chattanooga, TN--GA MSA | 90 | SE | 0
Tampa--St. Petersburg--Clearwater, FL MSA | 21 | SE | 0
Albany--Schenectady--Troy, NY MSA | 57 | NE | 0
Allentown--Bethlehem--Easton, PA MSA | 66 | MA | 0
Austin--San Marcos, TX MSA | 38 | SW | 0
Bakersfield, CA MSA | 65 | WC | 0
Baton Rouge, LA MSA | 70 | SE | 0
Boise City, ID MSA | 97 | WE | 0
Buffalo--Niagara Falls, NY MSA | 43 | NE | 0
Cincinnati--Hamilton, OH--KY--IN CMSA | 24 | MW | 0
Cleveland--Akron, OH CMSA | 16 | MW | 0
Colorado Springs, CO MSA | 81 | WE | 0
Daytona Beach, FL MSA | 83 | SE | 0
Dayton--Springfield, OH MSA | 53 | MW | 0
El Paso, TX MSA | 64 | SW | 0
Fort Myers--Cape Coral, FL MSA | 95 | SE | 0
Fort Wayne, IN MSA | 82 | MW | 0
Fresno, CA MSA | 54 | WC | 0
Grand Rapids--Muskegon--Holland, MI MSA | 48 | MW | 0
Greensboro--Winston-Salem--High Point, NC MSA | 37 | SE | 0
Harrisburg--Lebanon--Carlisle, PA MSA | 67 | MA | 0
Honolulu, HI MSA | 56 | WC | 0
Kalamazoo--Battle Creek, MI MSA | 92 | MW | 0
Kansas City, MO--KS MSA | 26 | SW | 0
Lakeland--Winter Haven, FL MSA | 84 | SE | 0
Lancaster, PA MSA | 89 | MA | 0
Lansing--East Lansing, MI MSA | 93 | MW | 0
Lexington, KY MSA | 86 | SE | 0
McAllen--Edinburg--Mission, TX MSA | 75 | SW | 0
Melbourne--Titusville--Palm Bay, FL MSA | 88 | SE | 0
Modesto, CA MSA | 94 | WC | 0
Oklahoma City, OK MSA | 49 | SW | 0
Omaha, NE--IA MSA | 61 | WE | 0
Pensacola, FL MSA | 100 | SE | 0
Philadelphia--Wilmington--Atlantic City, PA--NJ--DE--MD CMSA | 6 | MA | 0
Pittsburgh, PA MSA | 22 | MA | 0
Providence--Fall River--Warwick, RI--MA MSA | 40 | NE | 0
Rochester, NY MSA | 47 | NE | 0
Sacramento--Yolo, CA CMSA | 25 | WC | 0
San Antonio, TX MSA | 30 | SW | 0
San Diego, CA MSA | 17 | WC | 0
San Francisco--Oakland--San Jose, CA CMSA | 5 | WC | 0
Sarasota--Bradenton, FL MSA | 73 | SE | 0
Scranton--Wilkes-Barre--Hazleton, PA MSA | 68 | MA | 0
Springfield, MA MSA | 72 | NE | 0
St. Louis, MO--IL MSA | 18 | SW | 0
Stockton--Lodi, CA MSA | 76 | WC | 0
Syracuse, NY MSA | 60 | NE | 0
Tucson, AZ MSA | 58 | WE | 0
Wichita, KS MSA | 78 | SW | 0