## Sheet1
Carriers | Test Date | Test Result
VZW & North Coast PCS | Dec. 23- Jan. 6th | Complete
VZW & Western Wireless | Jan. 12th - Jan. 16th | Complete
VZW & CorrWireless | March 4 - March 10th | In progress
Nextel and Rural Cellular - Fax/Server | Feb 23rd - Feb 27th | Complete
Nextel and Rural Cellular - Verisign | March 8th - March 12 | In progress
Nextel and Midwest Wireless - Fax/Server | March 22nd - March 26th | Incomplete
Nextel and Midwest Wireless - Verisign | March 29th - April 6th` | Incomplete
Nextel and Cellular 1 | TBD | Incomplete
RCC & Nextel | Mar 8-12
RCC & USC | Apr 26-30
RCC & Western Wireless | May 10-14
RCC & Alltel | May 10-14
RCC & Sprint LTD | April
Alltel & West Virginia Wireless | Week of May 10th
Alltel & Viaero | Week of May 10th
Alltel & Cell One AZ | TBD
Alltel & Western Wireless | April 26th - April 28th
Western Wireless & Sprint PCS | TBD
Western Wireless & Nextel Partners | TBD
Western Wireless & USC | TBD
Western Wireless & Viaero | TBD
Western Wireless & T-Mobile | TBD
Western Wireless & Cingular | TBD
Western Wireless & VZW | TBD
Sprint LTD & USC | TBD
Note on C1: Note as "Complete", In Progress or "Incomplete"